## Sheet1
Conversion phases |  | Workflow | Workflow Enhancer | Utilities
CONDITIONS
Each conversion will progress through the following phases | Planning: During the Planning phase, the POC and team will gather background information, decide what the end result looks like, determine how the transition will be verified, and create and deconflict the conversion schedule.
Preparation: The Preparation phase includes data cleaning, build adjustments, configuration within the Atlassian tool suite, ClearQuest to Jira data mapping, and creation of labels and views for moving code from ClearCase to git.
Conversion: The Conversion phase is short and focused on migrating data using the work done during the Preparation phase.
Validation: The Validation phase is also short and focused. This phase clearly demonstrates that the migration was successful or that it was not. The outcome is either a shutdown of all work in the old tools or a rollback back to the Preparation phase.
Planning
Information to capture/develop | Product Map: diagram with all products for a program along with dependencies.
Product List: information for each product | product name current vob(s) location new repo name(s) branching strategy build instructions release instructions
Repo List | list of all repositories that will be used for this program (Excel). There is potentially a many-to-many mapping of repos to products that must be captured. Note that large binaries will be stored outside of git repos and must be identified (see next section).
Planning cont | Information to capture/develop cont
Version List: list of versions with enough detail to perform the conversion. This includes: Version name, used for tags Parent version ClearCase label name ClearCase view or config spec to access the files Pre-conversion verification method Post-conversion verification method
Preparation
Identify all large binary files in the build. | These include UI images, test data, third-party libraries, and build tools. These will be stored separately from source code in the new tools. Flag each build in the Product List if it includes large binary files. For each build with large binary files, decide how to update the build to allow for restructuring. The build should be updated before the Conversion phase. This may impact the length of the Preparation, Conversion, and/or Verification phase. Update and re-coordinate schedules as needed. | GIT LFS |  | GIT LFS MOVES THESE FILE TO ARTIFACTORY
Convert all SCM builds to use ClearCase views. This serves to validate the GITbuild model.
Document all current product builds. Create updated versions of build documentation to reflect the new build processes.
This needs to take into account any restructuring of repositories.
Create updated versions of the branching strategy documentation to reflect the new repository structures.
Conversion
Will perform the conversion. Conceptually, the process looks something like this: | Create a snapshot view for the root of the version tree. Import this as the first git version. | Scripted
Working through the tree: | for a version with one parent: check out the parent version create a branch if needed overlay files commit label | Scripted
For a version with two or more parents: | check out one parent create a branch if needed merge the other parent(s) overlay files commit label | Scripted
High level Clearcase/git transition | Clearcase “views” will be used take “snapshots” of the codebase, to be imported into GIT a “snapshot” at time.
A comprehensive list of view will need to be created for each moment in time that we wish to preserve when moved to GIT
Should not be done with “date” tags Should use “labels”
Releases, features, fixes, etc Could use branch “latest”
VALIDATORS
Validation | Date compare CC vs. GIT | Field has been modified | Custom messages for validator
Validation on linked issues | Date expression compare | Comment required |  | Issue Clone Post Function.
Validation on subtasks | Fields required, mandatory | Field is required |  | Assign Post Function.screen.
Users in a field is/isn't in a project role | Date within range | Previous status |  | Assign to Workflow Step Actor Post Function.
Check project property |  | Parent status
For the Verification phase, each version in the Version List will be verified per its Post-Conversion Verification steps. | (TBD)
POST-FUNCTIONS
Custom Fields
Location text field
Location select field
Direction field
OTHER
DART | Issue transition summary
Transition to Task tracking using Jira
OTBE | Implement Continuous Integration
Other consideration's | User lists View lists Release lists Branching structure Feedback on extent to which you require/need/want to preserve revision history Program and project timelines

## Sheet2
Each conversion will progress through the following phases:
·Planning: During the Planning phase, the POC and team will gather background information, decide what the end result looks like, determine how the transition will be verified, and create and deconflict the conversion schedule.
·Preparation: The Preparation phase includes data cleaning, build adjustments, configuration within the Atlassian tool suite, ClearQuest to Jira data mapping, and creation of labels and views for moving code from ClearCase to git.
·Conversion: The Conversion phase is short and focused on migrating data using the work done during the Preparation phase.
·Validation: The Validation phase is also short and focused. This phase clearly demonstrates that the migration was successful or that it was not. The outcome is either a shutdown of all work in the old tools or a rollback back to the Preparation phase.